WEEKLY REPORT — WEEK 44/2026

Project: Automated e-invoice retrieval (Tax portal → XML → PDF) using in-house captcha models

Period: 19–30 Oct 2026 (weeks 43–44)  ·  Figures as of 28 Oct 2026  ·  Compared with the week 42 report (figures as of 14 Oct)

# 1. Summary

- Captcha: 3 more providers trained successfully (Thai Son, the Tax portal – login model retrained, Dong Nam A). 15 of 24 providers done; 9 are training on another machine, expected by 31 Oct.

- PDFs via lookup links (from XML): 29 of 136 providers now return PDFs for real invoices (week 42: 11) → 18 more. 107 remain: 46 ready (adapter built, waiting for a real invoice to test) and 61 not done.

- PDFs via email: 32 of 136 providers (week 42: 6) → 26 more, plus 2 sellers outside the list (247Express, Fahasa). 104 remain: 44 ready and 60 not done.

- Original PDFs in the database: 1,361 — 837 via lookup links from XML, 476 from email attachments, 48 downloaded using links/codes in emails.

# 2. Captcha

Figures from the WBS2 sheet (docs/Danh_sach_NCC.xlsx) and real training runs (runs/<group>/history.csv, evaluate on the test set). Total: 15 done / 9 training / 24 providers.

## 2.1. Trained since week 42

| Group | Provider | Result (test) | Notes |
| --- | --- | --- | --- |
| g_600x120 | Tax portal (GDT login) | 87.30% (1,370 images); per character 97.79% | Retrained 16–17 Oct on 13,757 images (previously 1,784). In production for GDT login and POS invoice queries (sco-query now requires a captcha). |
| g_200x70 | Thai Son (einvoice.vn and dedicated portals: MM, Jollibee, Cong Vang…) | 89.24% (1,125 images); per character 97.24% | From 0% to 89% by fixing labels. Server accepted 19/22. The thaison adapter retrieves real PDFs (done 23 Oct). |
| g_180x50_tax24 | Dong Nam A (TAX24) | 98.99% (99 images); per character 99.80% | Trained 15 Oct on 1,000 images. This is the tax24.com.vn login captcha. |

## 2.2. Currently training (26–31 Oct, on another machine)

| Provider | Group | Current state | Notes |
| --- | --- | --- | --- |
| ASIA | g_150x30 | Adapter solves with ddddocr (server accepted 11/15) | Old model 0%; a dedicated model should raise the pass rate |
| VN-Invoice (vninvoice.vn) | g_180x50_vn | Upper/lower-case labels fixed 20 Oct, 56-character alphabet | Old model: 62% on test but 0/8 on live captchas (case errors) |
| VI NA (SmartSign) | g_150x39 | 3,253 labels reviewed by hand 26 Oct, 33-character alphabet | Adapter uses ddddocr (54/60) |
| PA Viet Nam | g_160x75 | Adapter solves with ddddocr (40/40) | Old model 0% |
| VNISC | 100x46 captcha, 6 digits | Adapter solves with ddddocr (20/20) |  |
| Bitware | g_70x23 | Old model 23.6% | No real invoice yet |
| Dong Sai Gon Telecom (VDSG) | g_250x40 | Training data generated with BotDetect | Portal requires login |
| Lac Viet | g_150x32 | Old model 0% | No real invoice yet |
| Public service portal | — | Training |  |

Each model brought back will be evaluated on the test set and on live captchas before it goes into an adapter. Note: WBS2 marks Ngo Gia Phat (g_200x80) as “Done”, but history.csv shows only 5.9% — to be reviewed.

# 3. PDFs via lookup links (from Tax portal XML)

| Metric | Providers | Providers / notes |
| --- | --- | --- |
| Retrieved (Done) | 29 / 136 | 837 PDFs in the database |
| – already by week 42 (14 Oct) | 11 | MISA, EasyInvoice, VNPT, Viettel, HILO, BKAV, VETC, M-INVOICE, My Software, Visnam, iPOS |
| – added in week 43 (19–23 Oct) | 8 | Vinh Hy, Minh Khang, CyberLotus, Thai Son, VI NA (SmartSign), FAST, PA Viet Nam, VNISC |
| – added in week 44 (26–27 Oct) | 10 | Mat Bao, Win Tech (WinInvoice), Phuong Nam (eVAT), Online VI NA, VININVOICE, Rosy, ASIA, MobiFone, KiotViet, WEBCASH (wetax) |
| Added since week 42 | 18 |  |
| Remaining | 107 |  |
| – Ready | 46 | Adapter built and portal checked; no real invoice to test yet. Planned 1–30 Nov 2026 |
| – Not done | 61 | Plan: 8 providers in November, 53 in December 2026. Reasons: reCAPTCHA/Turnstile (HT, EFY, FPT, CMC, TS24…), login-only portals, waiting for a captcha model, need one real lookup code |

PA Viet Nam, ASIA, MobiFone, KiotViet and WEBCASH can only be looked up with the code from the email (the Tax portal XML has no code).

# 4. PDFs via email

| Metric | Providers | Providers / notes |
| --- | --- | --- |
| Retrieved (Done) | 32 / 136 | 476 PDFs from attachments + 48 PDFs via links/codes in emails. Outside the list: 247Express, Fahasa |
| – already by week 42 (14 Oct) | 6 | M-INVOICE, Thai Son, Viettel, VNPT, HILO, VNISC |
| – added in week 43 (20–23 Oct) | 16 | Softdreams, MISA, BKAV, Visnam, iPOS, FPT, EFY, HT, Mat Bao, VN-Invoice, VI NA, FAST, PA Viet Nam, Online VI NA, Phuong Nam, VININVOICE |
| – added in week 44 (26–27 Oct) | 10 | Vinh Hy, Minh Khang, Win Tech, MobiFone, ASIA, TS24, Rosy, WEBCASH, VETC, KiotViet |
| Added since week 42 | 26 |  |
| Remaining | 104 |  |
| – Ready | 44 | Links/codes in emails are supported, but no real email from that provider yet. Planned 1–30 Nov 2026 |
| – Not done | 60 | Plan: 8 providers in November, 52 in December 2026 |

4,309 emails read (read-only). Links in emails: 2,904 downloaded; 1,651 skipped because the email already had the PDF attached; 705 pending (no adapter for the host yet, or a reCAPTCHA portal such as CMC).