## WECMS
WEEK | CLIENT | DESCRIPTION
16/10 ->22/10 | SCRAPING | 1. Captcha OCR - 107,364 labelled samples over 20 invoice portals - Usable : 12 models / 66,966 samples (10 of them 94-100%) - Trained this week : GDT login 13,757 samples -> 87.3% (54 epochs, ~40h) ; Thai Son 13,306 -> 89.2%, first working model for that portal - Re-training : VN-Invoice 11,632 samples - labels were wrong on upper/lower case, corrected this week ; Thai Son at higher resolution - Not usable yet : 8 portals / 40,398 samples - need more samples or label clean-up 2. Changed how invoices are pulled from the tax portal : take the whole list first (one "Export Excel" request per invoice type), then download each XML from that list (Done 10/20) -> the old way paged through the API while downloading, so invoices could be missed when the paging shifted 3. Invoice email reader (IMAP, read-only, never opens a link) : 68 mails scanned, 50 recognised as invoice mails - 28 attachments extracted : 17 PDF + 11 XML, including files inside .zip and forwarded .eml - 13 matched to invoices in the database (11 PDF + 2 XML) ; 14 were duplicates of what the tax portal already provided - 57 lookup links found : 16 fetched through the supplier adapters, 27 waiting for an adapter Current total : 1,012 invoices / 799 XML / 138 original PDFs through 11 supplier adapters Nextweek: -> Retrain the VN-Invoice captcha model on the corrected labels -> Build the Thai Son (einvoice.vn) PDF adapter - its captcha model is ready -> 232 invoices still have no PDF source : add adapters for the largest suppliers
| SETUP SEVER | - New server for the scraping job : Python 3.13 + dependencies installed (Done 10/21): Souce code: (192.168.60.13), DB:(192.168.60.121), link:(https://we-scraping.wetax.com.vn/login) - Scheduled task can now run while logged off, needed on a server with no interactive session Nextweek: -> Training template countine -> Checking the schedule

## NEW EMPLOYEE (hidden)
| DATE | CATEGORY | CONTENT | REMARKS | STATUS
22107/2025
| 2025-11-07 | TASK | Follow up WeCMS Multi Language fix | https://flow.team/l/1563u | In Progress
|  | TASK | System shows searched content from WABOOKS to WeCMS | https://flow.team/l/15Fle | Requested
| 2025-12-07 | TASK | Follow up Lumens Firm Banking Contract | https://flow.team/l/1fHb1 | In Progress
|  | TASK | Renew WeCMS Multi Languages files |  | In Progress
| 14/07/2025 | TASK | [LUMENS] Payment - Update Reporting Account field for Vendor / Expense Payments | https://flow.team/l/15WpJ | Done
|  | TASK | [LUMENS] Banking - Update Reporting Account field for Transaction History (VND & FCY) | https://flow.team/l/158go | Done
|  | TASK | [IMP] Contact function | https://flow.team/l/1fu5A | Done
| 15/07/2025 | TASK | Follow up Contract Firmbanking | https://flow.team/l/1fHb1 | In Progress
|  | TASK | [A1-01] UAT - Transfer Own Accounts > Input Transfer Amount | https://flow.team/l/1UaaA | In Progress
|  | TASK | [A1-02] UAT - Account Inquiry(FCY) > Excel dowload form imp | https://flow.team/l/1Uaq8 | In Progress
TASK
| 16/07/2025 | 번역 | AI 검색_기능명세서 | LINK | Done
|  | 번역 | [2025-05-15] 다글로 연동 | LINK
| 17/07/2025 | 번역 | 채팅 전달하기/게시글 인쇄/알림 안내_다국어 | LINK
|  | TASK | Meeting with BC Card
| 18/07/2025 | TASK | UAT Transaction History (VND & FCY) > Missing confirm date | https://flow.team/l/1UI5d
[ML] WeCMS Multi Languages fix
이번주 | 2025-07-07 | 번역 | AOS_구글 로그인 오류메시지 | LINK | Done
|  | 통역 | PO/CX Team (HAS TA) |  | Done
|  | 교육 | WeCMS 이해 |  | Done
|  | 통역 | PO/Marketing/Design Meeting Lookup Function on Landing Page |  | Done
| 2025-08-07 | 번역 | SK쉴더스_로그인감사_다국어 |  | Done
|  | 번역 | 푸쉬 숨김_기획 문서 | LINK | Done
|  | TASK | Follow up New Contact Popup Screen |  | Done
|  | TASK | Follow up Excel Templates for Up/Download | https://flow.team/main.act?detail | In-progress
|  | TASK | Follow up Contract Firmbanking | Shinhan and Lumens to sign Firm Banking Contract, waiting for Customer Identification Code | Urgent
|  | TASK | Visit Restaurant/Cafe for e-invoce issuance from POS |  | Pending
| 2025-09-07 | TASK | Meeting w Global Team (on Design/Publishing/Dev schedule) |  | Done
|  | TASK | WeCMS Multi Language Translation | LINK | In-progress
| 2025-10-07 | TASK | WeCMS Multi Language Translation | LINK | Done
|  | TASK | WABOOKS Operation Status Meeting |  | Done
차주 |  | TASK | Follow Lumens and Shinhan Firm Banking contract
|  | TASK | Follow up WeCMS Multi Language
|  | TASK | Follow up Excel Templates for Up/Download
| 2025-01-07 | 번역 | AI 검색_기능명세서 | LINK
| 2025-02-07 | 통역 | WeBill & WeTax Shop Connect | Purpose: WeBill's Biller who wants to issue E-invoice with WeTax or Other providers. Tab Name: E-invoice Config / Partner -> Provider Error message: When log in, if unsucessful, error message must be more detailed, show where error is so that Biller can easily change it. Details: Add tooltips to help Biller defines the meaning of the field they are using Bill List E-invoice Function: Complicated, need explaination of each status
| 2025-02-07 | 통역 | Sales Interview | Danang Interview Room
| 2025-02-07 | 통역 | Lumens 고객 방문 | Connect with Account PIC through Zalo (Forward WeCMS Vietnamese version)
| 2025-03-07 | 번역 | 1. 채팅 전달하기/인쇄/ 알림 기능 2. 오픈URL_기획문서 | LINK 오픈URL_기획문서
| 2025-04-07 | 통역 | BIDV 미팅 | Join meeting with BIDV PICs (WeCMS, WeBill)
| 2025-04-08 | 통역 | Sales Interview